## High-level sprint schedule
Epic One - Initial recommendation engine trial | [7 empty] | The goal of this Epic is to bring up an initial version of the recommender engine, and do basic A/B testing to see if the population targeted for the "treatment" shows an uplift in the number of skills downloaded and the amount of time spent using those skills
CRISP-DM Phase | Sprint | Story | T# | High Level Task Description | People Days | Dependencies | Skill Set Needed for task | Success Criteria | Risks | Notes
Business Understanding | 1 | Work with Business Partners to define the test population and criteria | [5 empty] | 1) Definition of the characteristics to sample defined by Marketing 2) Number of people to sample finalized (n) 3) Random sample of n customers meeting the criteria identified by GUIDs and assigned to test population for later A/B testing
|  | S1 | T1 | Define scope of test population and characteristics to sample | 5 |  | Business Analyst
|  | S1 | T2 | Pull random sample GUIDs that meet criteria | 10 | depends on T1 | Data Dev(s) |  |  | random sampling plan required for statistically valid inference of population
|  | S1 | T3 | Identify GUIDs for the A and B cohorts for later evaluation stages | 10 | depends on T2 | Data Dev(s) |  |  | will need to do testing against a control group, hence the A/B tests
| 1 | Inventory existing Alexa data sources | [5 empty] | 1) Per GUID skills downloaded in the last 120 days can be retrieved via function call to new procedure 2) Total time used per skill per GUID can be retrieved via function call to new procedure 3) Correct data returned is verified
|  | S2 | T4 | Build pipeline for querying usage by skill | 20 |  | Data Dev(s) |  |  | All Devs are familiar with the languages and tools being used, no risks are anticipated at this time
|  | S2 | T5 | Build pipeline for querying skills downloaded | 20 |  | Data Dev(s)
|  | S2 | T6 | Test/Verify results | 20 | Depends on T5 & T4 | Data Dev(s) and/or Data Scientist(s) |  |  | Can be done in parallel as partsof T4 &5 are done
Data Understanding | 1 | Setup access to external data sources | [5 empty] | 1) All team members working on the ASR project can access the "scrubbed" purchase data store 2) Programmatic access for new recommender is granted and working 3) Data relevant to the ASR algorithm are identified and documented
|  | S3 | T7 | Get Developer permissions established to the correct purchasing data source | 10 | Backlog in the team handling purchase data access | PM |  | External dependency on the purchasing team for getting data access. If training, vetting, or other process is needed this could take longer than expected. | Coordination with external groups is assumed to be a PM task
|  | S3 | T8 | Inventory and explore purchasing data to find the relevant items to import into project | 20 |  | Data Dev(s) and/or Data Scientist(s)
| 2 | Verify Data Quality | [5 empty] | 1) External and internal data conform to published specs 2) Data meet Service Level Agreements (SLA) for number of allowed incomplete records 3) Any non-compliance to "clean data" policy is noted for later mitigation
|  | S4 | T9 | For all data sources, verify the quality of incoming data, document needed cleaning if any | 30 |  | Data Dev(s), Data Scientist(s) |  | If external data is not as clean as owning team claims, data cleaning and/or mitigation could be required
Data Preparation | 2 | Create pipeline to bring purchase data to project | [5 empty] | 1) Per GUID data from Purchased Items is available to ASR pipeline on demand 2) query latency for per GUID information is within the SLA defined
|  | S5 | T10 | build import pipeline for select purchase data | 60 | depends on T9 | Data Dev(s)
| 3 | Create combined data set | [5 empty] | 1) Views of the data joining purchase data per GUID to per GUID skills downloaded & usage data are working 2) View data can be stored to ASR stores for model building
|  | S6 | T11 | Merge Purchase, Skills downloaded and Skills usage data into unified set | 20 | depends on T10 | Data Dev(s) and/or Data Scientist(s)
| 3 | Split dataset by cohort and function | [5 empty] | 1) Separate training (80%), validation (10%) and testing (10%) datasets are created 2) within each set, the A or B cohort membership is flagged
|  | S7 | T12 | Take the merged data set, split into train, validation (hold-out) and test data sets | 40 | depends on T11 | Data Dev(s) and/or Data Scientist(s)
Modeling | 3 | Method selection | [5 empty] | 1) Data science team has clear recommendation for modelling method to use 2) go/no-go meeting to review recommendation accepts "go" 3) metrics for model success are defined and published for approval
|  | S8 | T13 | Conduct preliminary experiments on the training data and select modelling method to move forward with | 40 | depends on T12 | Data Scientists
| 4 | Model Iteration 1 | [5 empty] | 1) Model is built 2) Model can run without failures
|  | S9 | T14 | Generate first model(s) | 40 | depends on T13 | Data Scientists
Evaluation | 5 | Model Iteration 1 Evaluation | [5 empty] | 1) Model metrics are generated and reviewed, based on appropriate measures for modelling method
|  | S10 | T15 | Evaluation of models from last sprint | 60 | depends on T14 | Data Dev(s) and/or Data Scientist(s)
| 5 | Model Iteration 1 Testing | [5 empty] | 1) Model performance on test data is within 2% accuracy of training data
|  | S11 | T16 | Test model if passed T14 | 40 | depends on T15 | Data Dev(s) and/or Data Scientist(s) |  |  | Will only move to A/B testing if model passes evaluation
Hard Process gate - cannot move to A/B testing or deployment until a model passes validation and testing. Repeat Sprints 4 & 5 as needed until this is achieved
Deployment | 6+ | A/B test candidate model | [5 empty] | 1) Average uplift in KPIs from the test cohort are within 5% of predicted values for the population that receives the "treatment"
|  | S? | T17? | Using the test population identified in T1, conduct A/B testing on the uplift of downloaded skills and usage time for recommendations | 60 | T1, T16 | team |  | Marketing will have to be ready to launch new "recommended for you" skills page | may take more than one sprint to full verify model
| TBD | Deploy successful model | [5 empty] | 1) model runs in data center, serves relevant results 2) model does not cause any impacts to service 3) Sustaining Engineering provides regular updates on the model performance
|  |  | TBD | Once a model has passes A/B test, it must be approved by chain of command for deployment | placeholder | above | PM coordinating w/management
|  |  | TBD | Once a model has been approved for deployment, deploy it | 40 |  | Data Devs
|  |  | TBD | Hand-off to Sustaining Engineering, who will monitor initial deployment | 20 |  | Sustain Engineer